## Project Plan
[6 empty] | Feb |  | March | [30 empty] | April
Requirement # | Requirement | Task # | Task | Estimate | Owner | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | UI/Backend-Create Main Pages | 1.1 | Create homepage | 2.5d | Lakshaye | bar: March 3; March 6 to March 7; March 9
|  | 1.2 | Create Group Poll/Meeting Selection Page | 2.5d | Arjun | bar: March 3; March 6 to March 7
|  | 1.3 | Create Group Poll Form Page | 2.5d | Lakshaye | bar: March 3; March 6 to March 7; March 10
|  | 1.4 | Create Meeting Form page | 2.5d | Arjun | bar: March 8 to March 10
|  | 1.5 | Designing the database schema | 2.5d | Venkatesh | bar: March 3; March 6 to March 7
|  | 1.6 | Create structure for backend development | 2+1d | Divya/Harshitha | bar: March 3; March 6 to March 7
|  | 1.7 | Create API to intitate poll | 3d | Divya | bar: March 8 to March 10
|  | 1.8 | Create API to store details of poll participants | 2d | Harshitha | bar: March 7 to March 8
|  | 1.9 | Modify retrieved database information to required response format | 2d | Harshitha | bar: March 9 to March 10
|  | 1.1 | Create schemas for the DB | 2.5d | Venkatesh | bar: March 6 to March 8
2 | UI/Backend-Calendar View | 2.1 | Create Calendar view to select slots | 2.5d | Arjun | bar: March 13 to March 15
|  | 2.2 | Create Recurring and intersection of slots view | 2.5d | Lakshaye | bar: March 13 to March 14
|  | 2.3 | Implement Procedure for invoking GET API to get participants slot selection data. | 5d | Arjun/Venkatesh | bar: March 13 to March 17
|  | 2.4 | Implement Procedure for submitting selected slots to POST API | 5h | Lakshaye | bar: March 15 to March 17
|  | 2.5 | Establish DB connection to the application | 2.5d | Venkatesh | bar: March 14 to March 16
|  | 2.6 | Create API POST method for account-wise calendar details | 3d | Divya | bar: March 15 to March 17
|  | 2.7 | Create API GET method for account-wise calendar details | 1d | Harshitha | bar: March 13
|  | 2.8 | Create API to create and store 1:1 or 1:many meetings | 1.5d | Harshitha | bar: March 13 to March 14
|  | 2.9 | Handle recurring events in calendar API | 2.5d | Harshitha | bar: March 14 to March 17
|  | 3.1 | API for Pending Meeting Request | 3d | Divya | bar: April 3 to April 5
|  | 3.11 | API for Finalizing Meeting Request | 2d | Divya | bar: April 6 to April 7
3 | UI/Backend-Confirmation page and Link sharing | 3.1 | Create Poll generated page | 2.5d | Arjun | bar: March 27 to March 29
|  | 3.2 | Create Meeting Generated Page | 5d | Lakshaye | bar: March 27 to March 31
|  | 3.3 | Implement procedure to POST details and GET shareable link for Poll | 2.5d | Arjun | bar: March 29 to March 31
|  | 3.4 | Implement procedure to POST details and GET shareable link for Meeting. | 2.5d | Lakshaye
|  | 3.5 | Normalization of relations | 5d | Venkatesh | bar: March 27 to March 31
|  | 3.6 | Unique Meeting ID Generation - R&D | 2d | Harshitha | bar: March 27 to March 28
|  | 3.7 | Generate Unique link for poll/meeting | 3d | Harshitha | bar: March 29 to March 31
|  | 3.8 | OTP Generation - R&D | 2d | Divya | bar: March 27 to March 28
|  | 3.9 | Mail verification when entering mail ID for Poll | 2d | Divya | bar: March 29 to March 30
4 | UI/Backend-Registration and Login Page | 4.1 | Create Registration Page | 2.5d | Lakshaye | bar: April 3 to April 5
|  | 4.2 | Implement functions to post data to backend | 2.5d | Lakshaye | bar: April 5 to April 7
|  | 4.3 | Create Login Page | 2.5d | Arjun | bar: April 3 to April 5
|  | 4.4 | Implement functions to retrieve and validate user login details. | 2.5d | Arjun | bar: April 5 to April 7
|  | 4.5 | Create SQL statements to store data from backend | 2.5d | Venkatesh | bar: April 3 to April 5
|  | 4.6 | Create API to Create Account | 2d | Divya | bar: March 13 to March 14
|  | 4.7 | Create API for Login | 2.5d | Harshitha | bar: April 3 to April 5
|  | 4.8 | Mail verification when creating account and logging in | 1d | Divya | bar: March 31
|  | 4.9 | Implementing Database Indexes/triggers | 2.5d | Venkatesh | bar: April 5 to April 7
|  | 4.1 | Handle Session Management | 2.5d | Harshitha | bar: April 5 to April 7
5 | UI/Backend-Meeting modification | 5.1 | Create Modification View | 2.5d | Lakshaye | bar: April 10 to April 12
|  | 5.2 | Implement function to update changes to backend | 1.5d | Lakshaye | bar: April 13 to April 14
|  | 5.3 | Create Utilities View | 2.5d | Arjun | bar: April 10 to April 12
|  | 5.4 | Create pop-view to create task,reminders etc. | 1.5d | Arjun | bar: April 12 to April 14
|  | 5.5 | Implement procedures to post and retreive data | 1.5d | Lakshaye/Arjun | bar: April 14
|  | 5.6 | Create a modification API for meeting | 3d | Harshitha | bar: April 10 to April 12
|  | 5.7 | Handle pending request in case there is meeting update | 2d | Divya | bar: April 10 to April 11
|  | 5.8 | API for Delete poll | 2d | Harshitha | bar: April 13 to April 14
|  | 5.9 | API for Finalize poll | 3d | Divya | bar: April 12 to April 14
|  | 5.1 | Virtual Setup | 5d | Venkatesh | bar: April 10 to April 14
7 | Testing | 7.1 | Create and test validation of values | 5d | Arjan/Lakshaye/Venkatesh/Harshitha/Divya
|  | 7.2 | Create Style Guide | 5d
|  | 7.3 | Execute User Tests | 5d
|  | 7.4 | Revise documentation | 5d
|  | 7.5 | Prepare Presentation | 5d
Lakshaye
Arjun
Divya
Harshitha
Venkatesh

## Test Plan
2.1 | User can add or edit courses
1. Navigate to the "course management" screen from the main menu 2. Click on the plus icon in the top left of the scren 3. Enter the following information : CSE 611, Fall 2022, Alan Hunt 4. Click "Add Class" 5. The class should appear in the list of courses for fall 2022
1. Navigate to the "course management" screen from the main menu 2. Click on the course "CSE 611" 3. Change the instructor name to "John Doe" 4. Click "Save" 5. Verify that in the course listing, the instructor now says John Doe
2.1.1 | Verify that the "course listing" appears when the user clicks on "course management"
2.1.2 | Verify that on the course management screen, the plus icon appears. Clicking on the plus icon should bring up a modal dialog with fields for course name, course number, semester and instructor
2.1.3 | Verify that clicking on a course in the course listing brings up a modal dialong with the fields course name, course number, semester, and instructor Verify that all information in these fields is prefilled with the current values
2.1.4 | Verify that only valid semester values can be chosen for semesters verify that only valid instructors can be chosen for course instructors verify that duplicate courses create a warning
1.1 | User needs to sign up on OES
To verify if the new sign up page appears when user clicks "Create account" if he doesn't have an account
If the user already exists, provide email id and password to login to the account.
Forget password button verifies user email address and provides option to change password.
1.1.1 | Verify that the create account page takes details from user and stores in the DB
2.1 | Create poll feature
Clicks Create Poll Button -> Navigate to the screen to provide Event name, Description and location of the meeting.
Clicks Create Poll Button -> Should be able to select Dates and duration of the meeting.
Clicks Create Poll Button -> Able to select the time slots for the meeting
2.1.1 | Verify that all provided durations can be selected by the user.
Verify if the user is able to select weekly or monthly view for date selection
Verify different calender views when user clicks the claender view dropdown.
3.1 | Create meeting feature
Clicks Create meeting Button -> Should be able to select Dates and duration of the meeting.
Clicks Create meeting Button -> Able to select the time slots for the meeting
3.1.1 | Verify that all provided durations can be selected by the user.
Verify if the user is able to select weekly or monthly view for date selection
Verify different calender views when user clicks the claender view dropdown.